## Sheet1 (2)
| Start Date | Duration
Planning Meeting | 2007-04-09 | 1
Develop Questionnaire | 2007-04-10 | 11
Print and Mail Questionnaire | 2007-04-24 | 9
Receive Responses | 2007-04-27 | 15
Data Entry | 2007-04-27 | 18
Data Analysis | 2007-05-15 | 4
Write Report | 2007-05-21 | 12
Distribute Draft Report | 2007-06-04 | 2
Solicit Comments | 2007-06-05 | 5
Finalize Report | 2007-06-11 | 6
Distribute to Board | 2007-06-18 | 2
Board Meeting | 2007-06-26 | 1

## Download Session
Click to view Macro Video
Click to view Function Video
Click to Download Android application for Excel Function
Click to Download Android application Excel VBA {Macro}
www.excelprince.com
click the Below Icons
What our Student Speak

## Excel FunctionLink
Please contact for the Best Coaching of Advance Excel, Functions,VBA-Macro, MS-Access, SQL @Prince - 9953872217 |  |  |  | Links for Advance Excel Functions- Video
Sr. No. | Functions Name | Quantity | Link
1 | IF, And, Or (Operator) - (Excel Function with Prince) | 3 | https://www.youtube.com/watch?v=yOuAme8gDn4
2 | Advance Excel Function @ Prince Sethi | 1 | https://www.youtube.com/watch?v=pubZmXGiFgg
3 | Vlookup Part -1 (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=nyQ3ygES3vQ
4 | Vlookup - Part 2 (Absolute, Relative Reference) -(Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=y1d50FQB99Y
5 | Vlookup - Part 3 (Absolute, Relative, Mixed Reference) -(Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=pVCXYpcHY8w
6 | IsError, IfError, IsErr, ISNA, IsRef (Excel Function with Prince) | 6 | https://www.youtube.com/watch?v=YC0MetXqSKI
7 | Countif - Wild Card (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=A19gDhgwflw
8 | Today, Now, Edate (Excel Function with Prince) | 3 | https://www.youtube.com/watch?v=NJtz5Sh4TKY
9 | Exact (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=1DiJfvGdLQE
10 | Convert (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=3gBnzqx2xsE
11 | Network, Workday (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=tojUNhdktqo
12 | SumProduct (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=lw4lnJs6OvE
13 | SubTotal (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=KgmyZ0tLCHE
14 | Substitute, Replace, Rept, Value (Excel Function with Prince) | 4 | https://www.youtube.com/watch?v=juj-sNQjXBk
15 | Concatenate (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=5ZTuSLlNqrM
16 | Find, Left, Trim, Mid, Len (Merging of Functions)-(Excel Function with Prince) | 6 | https://www.youtube.com/watch?v=GQ0s86-K34U
17 | DB - Depriciation-Appriciation (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=KQBs0ss8rZQ
18 | Index, Match (Index-Match) (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=TKrgEsk4Lxs
19 | Cummulative Sum, Using Range Name in Function (Prince) | 1 | https://www.youtube.com/watch?v=l006ZnrY0Cc
20 | Dcount (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=HR0u8zxmiqQ
21 | Dcount, DcounA, DMax, DMin, Daverage, DSum (Excel Function with Prince) | 6 | https://www.youtube.com/watch?v=R8QmQH3VtMY
22 | Combin-Permut (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=0W8fUSZMc48
23 | Rept, Clean (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=OmuVeWUC31Q
24 | Round, Roundup, RoundDown (Excel Function with Prince) | 3 | https://www.youtube.com/watch?v=onVE1AFRpOQ
25 | Fact, Sign, Mod, Power (Excel Function with Prince) | 4 | https://www.youtube.com/watch?v=VbYrjyjvGh0
26 | LCM, GCD (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=hchRpwmTKFk
27 | Roman, Even, Odd, Abs (Excel Function with Prince) | 4 | https://www.youtube.com/watch?v=SiQpI0vb9sE
28 | Rand, Randbetween, Quotient, Mod, Pi (Excel Function with Prince) | 5 | https://www.youtube.com/watch?v=k4Ka6Y0bLYA
29 | Hour, Minute, Second, Time (Excel Function with Prince) | 4 | https://www.youtube.com/watch?v=xtkWlx9RXHQ
30 | Day, Month, Year, Date (Excel Function with Prince) | 4 | https://www.youtube.com/watch?v=W_tfxS_GVmE
31 | Count, CountA, Countblank (Excel Function with Prince) | 3 | https://www.youtube.com/watch?v=R63wE-mK9oI
32 | IsBlank, IsEven, IsOdd, IsLogical (Excel Function with Prince) | 6 | https://www.youtube.com/watch?v=Ob0j9sZH8b8
33 | IsNumber, Is Text , Validation (Excel Function with Prince) | 2 | https://www.youtube.com/watch?v=tADofsYBfUQ
34 | Datedif (Excel Function with Prince) | 1 | https://www.youtube.com/watch?v=3KuCYhnVqJ4

## Macro Links
Please contact for the Best Coaching of Advance Excel, Functions,VBA-Macro, MS-Access, SQL @Prince - 9953872217 |  |  | Links for Advance Excel VBA (Macro)- Video
Click to Download [Excel Function - Android Application ]
Click to Download [Excel VBA Macro - Android Application ]
Sr. No. | Macro Name | Link |  | File Download Link
1 | Basic Understanding of Macro [Worksheet, Range, Cells, Columns,Rows] | https://www.youtube.com/watch?v=JnOj3JWODh0&index=2&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcNDlvVTZmWDl2VkE/edit?usp=sharing
2 | Learn If, Else-if, Nested Elseif, Nested ifs | https://www.youtube.com/watch?v=6YSyg14tm-s&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dceUxNTFF3Ukd4TlE/edit?usp=sharing
3 | While Loop with Examples | https://www.youtube.com/watch?v=j-78MCYxdr0&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcaFVNZ1NtS2FmWWM/edit?usp=sharing
4 | Lets Learn For Loop with Different-2 Example | https://www.youtube.com/watch?v=r7dQkzwE_5s&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcSXNvRlg3cDU3VEE/edit?usp=sharing
5 | Lets Learn Nested For Loop , Dual For loop | https://www.youtube.com/watch?v=JvpW9ArNBX8&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcV0pzSmM0ZnhfZ1E/edit?usp=sharing
6 | Lets Learn For Each Loop | https://www.youtube.com/watch?v=Um-bw5x9wNc&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcRmJIaHZ4b1pxcDA/edit?usp=sharing
7 | Extract Content from Notepad to Excel Spreadsheet | https://www.youtube.com/watch?v=dYBUUZQUfUo&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcSExNSFR0MGxZUkE/edit?usp=sharing
8 | Filter data from a sheet and distribute it another sheets | https://www.youtube.com/watch?v=jOiMxAEPz4A&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcTl91bE1URUtvNTg/edit?usp=sharing
9 | Create Customize Function in VBA (Macro) - Function Procedures | https://www.youtube.com/watch?v=bhCVwGuT2QI&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dccDVtMFFxVWg3bkk/edit?usp=sharing
10 | Customize function to Count Colour in a given Range - function Procedure part 2 | https://www.youtube.com/watch?v=TbIxyjKJmCY&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcZ3NrN1JUVjZxOGc/edit?usp=sharing
11 | How to Identify last row/column in a data [ 3 Example ] | https://www.youtube.com/watch?v=Q2LXzn_s7b8&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcaWJHa0YyVG9vTzg/edit?usp=sharing
12 | Special Cells their customization | https://www.youtube.com/watch?v=OlvAk7jE0eM&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcZVlCLWdQal90STQ/edit?usp=sharing
13 | Select Case - Calling Function & Subprocedures | https://www.youtube.com/watch?v=RilZXofLtyY&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcc0s1cDY5U0V2YzA/edit?usp=sharing
14 | Select case and Calling Function Procedure - Part 2 | https://www.youtube.com/watch?v=Pi7OixGdZLQ&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcdkZzSWZ3d3dmVTQ/edit?usp=sharing
15 | Customize function to put function Text into comment | https://www.youtube.com/watch?v=gB_nKuoc7r8&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcZ0VTTGNfalI3eDA/edit?usp=sharing
16 | Deals With File Attributes through VBA | https://www.youtube.com/watch?v=ouJ8O5nhMEg&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcQjV6UmxHOXdvSDg/edit?usp=sharing
17 | Create an index page by using for Loop | https://www.youtube.com/watch?v=QOM1HVhUKZw&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcMWtsWEtnUS1ybUU/edit?usp=sharing
18 | Function Procedure to Extract numeric or Text part in Alphanumeric String | https://www.youtube.com/watch?v=rOjMel-cz2c&list=PL8eHn_8Mq2toWu7e5EJ2cGuwhZqlCZ1f0 |  | https://drive.google.com/file/d/0B1XLV4eCY-dcQVhVT0tCNE5zYXM/edit?usp=sharing
Finally the wait is over here we have two Android Applications
1. Learn Excel Function
2. Excel VBA (Macro)
Download and Learn Free of Cost....